## Action Plan - Weekly
Action Plans - Weekly Review by Management
| 1 | Description | Status | Opening Date | Closing Date
| 1.1 | Meeting with Software Company | Open | 2015-11-01
| 1.1.1 | To know about Software | Open |  |  | To take appointment for meeting
| 1.1.2 | Discussing time frame | Open |  |  | To take appointment for meeting
| 1.1.3 | Discussing Requirements | Open |  |  | To take appointment for meeting
| 1.1.4 | Discussing supplier to integrate TERASOFT and ODOO | Open |  |  | To take appointment for meeting
| 1.1.5 | Discussing Price | Open |  |  | To take appointment for meeting
| 1.1.6 | Final Contract | Open |  |  | To take appointment for meeting
| 1.2 | COA | Open | 2015-11-01
| 1.2.1 | Creating COA for MFI | Open |  | 2016-01-31
| 1.2.2 | Creating COA for LGC | Open |  | 2016-01-31
| 1.2.3 | Sending, Reviewing and Finalising | Open |  | 2016-02-01
| 1.2.4 | Hand over and set up in software | Open |  |  | To discuss with ODOO
| 1.2.5 | Checking the software | Open |  |  | To discuss with ODOO
| 1.3 | Loan Provision and Loan Write-Off | Open | 2015-11-09
| 1.3.1 | Comparing FRD's Policy and Company's Policy | Open |  | 2015-11-11
| 1.3.2 | Approving Final Policy | Open |  | 2015-11-11
| 1.3.3 | Creating Loan provsion and write-off | Open |  | 2015-11-15
| 1.3.4 | Hand over and set up in software | Open |  | Dec | To discuss with ODOO
| 1.3.5 | Checking the software | Open |  |  | To discuss with ODOO
| 1.4 | GL Intergration | Open | 2015-02-01
| 1.4.1 | Analysing the flow of TERASOFT | Close |  | 2015-05-02
| 1.4.2 | Preparing the policy for GL Integration | Close |  | 2015-02-15
| 1.4.3 | Reviewing and Finalising the policy | Close |  | 2015-02-20
| 1.4.4 | Hand over and set up in software | Open |  | 2015-02-21
| 1.4.5 | Checking the software | Open |  |  | To discuss with ODOO
| 1.5 | Payment Workflows | Open | 2016-01-20
| 1.5.1 | Discussing to Understand the relation of MFI and MMM | Open |  | 2016-01-20
| 1.5.2 | Preparing Payment Workflows | Open |  | 2016-01-27
| 1.5.3 | Reviewing and Finalising the workflows | Open |  | 2016-01-31

## Business Platform
Group's Business Platform (MFI /LGC)
Business Platforms
| Data Recording & Processing Platform |  | Group's GL Modules |  | Customer's Module
|  | Main functions | Accounting | HRM & Procurement | Scheme's
|  | Used for | MFI | Group's business | MFI - Business | "Real time" basis
|  | Software | "ODOO" |  | Terasoft |  | Payment partners
| Reporting Portals |  | External reporting | Consolidation & Internal reporting | SBV's Reporting |  | (MOMO/PAYOO)
|  | Main functions | FRD Reports | Management reports | Automatic & Electronic Reports
|  | Used for | MFI | Group's business | MFI - Business
|  | Software | "ODOO" | "FAST" | "MicroReport - SBV reporting Software"
|  |  | There is Reporting Format hardcopy issued by FRD | (To be done later) | Report is generated automatically
|  |  | FRD |  | (User code is required for sending to SBV's port)
Internal reporting's portal
SBV's Portal
|  |  | Documents | Key notes for MFI | Key notes for Legal | Priority | Contract
1/ | Group's GL Modules
1/ | "ODOO"
| - Financial Module |  |  | Set Up COA "Auto" Intergration with TERASOFT "Auto" Reports (FRD) | Set Up COA "Auto" Intergration with TERASOFT "Auto" Reports
| _Financial Management Module |  |  | Training User Manual
| - Software update during the first year (new version Migration) |  |  | Should record and discuss the new requirements during the first year | Should record and discuss the new requirements during the first year

## Scope of work (hidden)
| Flatforms | Main Responsibility | Advisor |  | Intergarted | Finstar
1 | Group's GL Modules | FAST | MAZARS |  | TERASOFT | Chief Account as Co-ordinator/End User
2 | Customer's Module | TERASOFT |  |  |  | Chief Account - key focus
2 | External reporting | FAST | MAZARS |  |  | Chief Account as Co-ordinator/End User
3 | Consolidation & Internal reporting | FAST |  | Group's Finance | TERASOFT | Chief Account as Co-ordinator/End User
5 | SBV's Reporting | IT - Supplier |  |  | TERASOFT | Chief Account - key focus

## Key actions to be done (hidden)
Group's Business Flatform (MFI / Social Fund/ Enterprises) |  |  | Business run (Target) | 2015-06-01
[7 empty] | Apr | May | [27 empty] | Jun |  |  |  | Jul
| No. | Main Tasks / Key deliverables | Finstar | Suppliers | Start date | Deadline | 20 - 27 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Data Recording & Processing Platform | 1.1 | Group's GL Modules
| 1.1.1 | Define & set-up "Chart of Accounts" for Groups in according to SBV/VAS/Tax… | Chief Account | Marzars | 2015-05-11 | 2015-05-15
| 1.1.2 | Define "LAC" entry booking diargram in accordance with VAS/Tax/SBV requirements | Chief Account | Marzars | 2015-05-06 | 2015-05-15
(Entry booking : Loan/ Certificate Fee/ Application Fee/Tax/Provision/ Loan Classification…)
| 1.1.3 | System intergration for GL posting of LAC transactions (Between TERASOFT & FAST) | Chief Account | Marzars + TERASOFT + FAST | 2015-05-11 | 2015-05-21
| 1.1.4 | System intergration for GL posting of LAC transactions (Between TERASOFT & PARNERS if any) | Chief Account + Business Team | Marzars + TERASOFT + FAST |  | TBC
| 1.1.5 | Data verification & reconciliation between TERASOFT & FAST for "LAC" booking entries | Chief Account | Marzars + TERASOFT + FAST | 2015-05-21 | 2015-05-25
| 1.1.6 | HRM Module (Paper Workflows/System implementation) | HR | FAST | TBC | TBC
| 1.1.7 | Payment procurement | Procurement | FAST | TBC | TBC
| 1.1.8 | User Acceptance Test (UAT)
|  | - GL Module for Accounting (GL Booking to FAST) | Chief Account | Marzars + TERASOFT + FAST | 2015-05-25 | 2015-05-30
|  | - HRM & Procurement | HR /Procurement | FAST |  | TBC
| 1.1.9 | "Go-Live" Decision
|  | - GL Module for Accounting (GL Booking to FAST) | Management | Marzars + TERASOFT + FAST |  | 2015-05-31 | [37 empty] | Must be done
|  | - HRM Module | Management | FAST |  | TBC
|  | - Procurement Module | Management | FAST |  | TBC
| 1.2 | Customer's Module
| 1.2.1 | Product's description (In accordance with MFI business/LAC scheme) | Business Team |  |  | 2015-05-04
| 1.2.2 | Definition of "Primary data Fields" for
|  | - System intergration with FAST (for GL posting automatically) | Chief Account | FAST | 2015-05-04 | 2015-05-08
|  | - System intergration with SBV'S Reporting tool (for SBV'S electronic report) | Chief Account | IT suppler + TERASOFT | 2015-05-04 | 2015-05-08
|  | - Internal reporting purposes | Group's Finance | FAST |  | TBC
| 1.2.3 | System Implementation for MFI Business
|  | - For managing LAC scheme's businesses | Chief Account + Business Team | Terasoft | 2015-05-08 | 2015-05-21
|  | - For intergration with FAST/SBV's reporting tool | Chief Account + Business Team | FAST + TERASOFT + IT Supplier | 2015-05-08 | 2015-05-22
| 1.2.4 | User Acceptance Test (UAT) | Business Team | Terasoft | 2015-05-22 | 2015-05-30
| 1.2.5 | "Go-Live" Decision | Management | Terasoft |  | 2015-05-31 | [37 empty] | Must be done
Reporting Portals | 2.1 | External reporting
| 2.1.1 | External reporting requirements (Lists/Templates/….) for Tax Authority/ Statistic office ... | Chief Account | Marzars | 2015-05-04 | 2015-05-07
| 2.1.2 | Users' Descriptions for system coding & implementation | Chief Account | Marzars + FAST | 2015-05-07 | 2015-05-11
| 2.1.3 | System Implementation | Chief Account | Marzars + FAST | 2015-05-11 | 2015-05-25
| 2.1.4 | User Acceptance Test (UAT) - Tax reports must be approved "ONLINE" before submission | Chief Account | Marzars + FAST | 2015-05-25 | 2015-05-30
| 2.1.5 | "Go-Live" Decision | Management | Marzars + FAST |  | 2015-05-31 | [37 empty] | Can be late within 1-2 weeks
| 2.2 | Consolidation & Internal reporting
| 2.2.1 | Consolidation requirements (Entity Level/ Product Level…) | Group's Finance | FAST | 2015-05-04 | 2015-05-11
| 2.2.2 | Internal reporting requirements (Financial performance IFRS/ Risk Management…) | Group's Finance | FAST | 2015-05-04 | 2015-05-11
| 2.2.3 | System Development & Implementation | Group's Finance | FAST | 2015-05-11 | 2015-06-15
| 2.2.4 | User Acceptance Test (UAT) | Group's Finance | FAST | 2015-06-16 | 2015-06-30
| 2.2.5 | "Go-Live" Decision | Management | FAST |  | 2015-07-01 | [37 empty] | To be reviewed
| 2.3 | SBV's Reporting
| 2.3.1 | SBV's reporting requirements | Chief Account
| 2.3.2 | Valuation & decision on IT supplier | Management |  | 2015-04-22 | 2015-04-27
|  | Contract signed | Management |  |  | 2015-05-08
| 2.3.3 | System Implementation
|  | - Database & Report design | Chief Account | IT suppler | 2015-05-11 | 2015-05-29
|  | - Software Coding & Testing | Chief Account | IT suppler | 2015-05-11 | 2015-05-29
|  | - Software/Network installment for electronic submission to SBV's portal | Chief Account | IT suppler | 2015-05-25 | 2015-05-29
| 2.3.4 | User Acceptance Test (UAT) | Chief Account | IT suppler | 2015-05-29 | 2015-05-30
| 2.3.5 | "Go-Live" Decision & 24/7 support for start-up periods (1->6 months) | Management | IT suppler |  | 2015-05-31 | [37 empty] | Must be done

## {TERASOFT} - Primary Fields (hidden)
[TERASOFT] - PRIMARY FIELDS FOR MFI BUSINESS as end-user | [5 empty] | Terasoft must store these fields for at leat SBV's reporting purpose of Lending Activities
If Terasoft is used for recording fundings (deposits) of customers, Other fields must be defined
(Detailed Fields should be done by Terasoft & IT Suppliers for 100% Accuracy of needs)
Used for
No. | Type | Primary fields | [5 empty] | SBV's Reporting tool | [FAST] - GL posting | [FAST] - Internal Reporting
1/ | Customer data for Lending business
|  | Full Name | ID. No | Actual living address | Date of birth | Telephone | Occupation (if any) | x |  | TBC
|  | Bank's account | [7 empty] | TBC
2/ | Contractual data for Lending Business
| Contract | Contract No. | Issued date | Due Date | Loan's purpose |  |  | x |  | TBC
| Loan | Currency | Loan amount | Paid Amount | Loan balance amount (Loan minus Paid amount) | Type of Loan (For provision) |  | x | x | TBC
| Interest | Interest rate | Overdue Interest rate | Interest accrued | Overdue interest Accrued | Interest - Paid Amount | Interest - Balance amount | x | x | TBC
| Fee | Application fee due/ paid | Service Fee due/paid | Late payment fee due/paid | Early payment fee due/paid | Prolongation fee due/paid |  |  | x | TBC
| Provision | Specific provision | General provision |  |  |  |  | x | x | TBC
| Payment date | pay date - Loan | pay date - Interest |  |  |  |  | x |  | TBC
| Sale | Saleman's ID | [5 empty] | x |  | TBC
3/ | Data used for system Intergration
|  | GL Code | [5 empty] | x | x | x
|  | GL Code | as Primary/Key field for intergration purpose (Mapping) between Different Systems

## Accounting Policy Platform (hidden)
[Group] Key Accounting Policy
| No. | Key accounting policies | Applied for | Prepared/Reviewed by | Approved by | Start date | End | Status | Ref
| 1 | GL system
| 1.1 | [MFI] Chart of Account (FAST & TERASOFT) | MFI | Chief Account | CEO | 2015-05-11 | 2015-05-25 | Done | 1.1 COA_Terasoft'!A1
| 1.2 | [Group] Chart(s) of Accounts (Under VAS) | Group | Mazars + Chief Account | CEO | 2015-05-25 | 2015-05-30 | To be advised by Mazars
| 1.3 | [Group] GL Intergration policy for key transactions | Group | Mazars + Chief Account | CEO | 2015-05-25 | 2015-05-30 | To be advised by Mazars
| 1.4 | [MFI] Accounting booking diagram for Micro-finance transactions | MFI | Mazars + Chief Account | CEO | 2015-05-22 | 2015-05-30 | Done | 1.4 Entry diagram'!A1
| 1.5 | [Group] Cost center - Policy | Group | Mazars + Chief Account | CEO | 2015-05-06 | 2015-05-08 | Done | 1.5 Cost Center'!A1
| 2 | Loan policy
| 2.1 | [MFI/LGC] Loan product & business process descriptions | Group | Alexandrov | Management |  | 2015-05-30 | Done | Product Parameters'!A1
| 2.2 | [MFI] Loan classification & Provision | MFI | Chief Account | Management | 2015-05-06 | 2015-05-15 | Done | 2.2 Loan provision'!A1
| 2.3 | [MFI] Loan write-off policy | MFI | Chief Account | Management | 2015-05-25 | 2015-05-30 | Done | 2.3 Loan write-off'!A1
| 3 | Finance & accounting policy
| 3.1 | [MFI] Business Workflows & GL Reconcilation for business partners | MFI | Chief Account | Management | 2015-05-18 | 2015-05-30 | Done | 3.1 Payment Workflows'!A1
| 3.2 | [MFI] Funding Procedure for Collection/Payment Vendors | MFI | Chief Account | Management | To be done | >= Jun 30
| 3.3 | [Group] Standard Policies for Opening & Reconcialtion of Bank Accounts | Group | Chief Account | Management | To be done | >= Jun 30
| 3.4 | [Group] Budget planning & Control Procedure | Group | Chief Account | Management | To be done | >= Jul 31
| 3.5 | [Group] Approval hierachy/Limit for Approvers | Group | Chief Account | Management | To be done | >= Jul 31
| 3.6 | [Group] Budget verification & Payment guideline for operational costs | Group | Chief Account | Management | To be done | >= Jul 31
| 3.7 | [Group} Reconcilation & Payment guideline for internal transactions | Group | Chief Account | Management | To be done | >= Jul 31
| 4 | Reporting regualtions
| 4.1 | [Group] Tax reporting | Group | Chief Account | CEO | 2015-05-18 | 2015-05-30 | Done | 4.1 Tax'!A1
| 4.2 | [MFI] SBV reporting guideline | MFI | Chief Account | CEO | 2015-05-18 | 2015-05-30 | Done | 4.2 SBV'!A1

## {TERASOFT} (hidden)
<TERASOFT> BUSINESS DEVELOPMENT REQUIREMENT FOR ACCOUNTING SET-UP
A/ | Business development Requirements |  |  | Status | Notes
1/ | Customer information
| - Manage each customer's data (based on product parameters) |  |  | Confirmed by TERASOFT
2/ | Collection/Disbursement channel |  |  |  | 3.1 Payment Workflows'!A1
| - Each (channel) vendor will have a "unique ID" among Terasoft |  |  | Confirmed by TERASOFT
| - Each vendor's ID should be attached by a "GL Code" |  |  | Confirmed by TERASOFT
| - Each transaction (Cash inflows & outlows) will be attached by Vendor's ID |  |  | Confirmed by TERASOFT
| - Terasoft must be interfaced with Vendor's system for data (Cash inflows/Outflows) integration |  |  | To be confirmed by Terasoft
| - Each transaction (Cash inflows & Cash outlows) will be attached by Client's contract |  |  | Confirmed by TERASOFT
| - Each transaction (Cash inflows & Cash outlows) will be defined "Double-Entry" in the "Body" table |  |  | Confirmed by TERASOFT
3/ | GL Code & Entry rule
3.1 | GL code |  |  | Confirmed by TERASOFT
- GL Code (COA) will be defined by MFI's accountant, and managed by IT Admin
3.2 | Entry rule :
- Each financial transactions shall be recorded as "double entry" (included GL code) basis
| - IF one payment is for one Account: |  |  | Confirmed by TERASOFT
| GL entry (Per transaction) : | Debit - CASH | 120
|  | Credit - Loan | 120
| - IF one payment is for many Accounts |  |  | Confirmed by TERASOFT
| GL entry (Per transaction) : | Debit - CASH | 100
|  | Credit - Loan | 100
| GL entry (Per transaction) : | Debit - CASH | 20
|  | Credit - Interest | 20
| - FOR "End of day" transaction (after end of day calculcation is done) |  |  | To be confirmed by Terasoft
| GL entry (Per end of day) : | Debit - Interest Accruals | 3
|  | Credit - Income | 3
3.3 | Data requirements
| Data should be recorded at 2 types of level. |  |  | To be confirmed by Terasoft
- Detailed (Contract) level : By customer/ By Payment Vendor with "seperately-defined" GL
- Total (GL) level : Total value for all transactions/ each type of transaction/a period of time (per day)
4/ | Accounting rule
4.1 | Loan disbursement to customer
| - [Per loan] Detailed record for each client / each payment vendor |  |  | Confirmed by TERASOFT
| - GL entry rule to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of loan : Principle/ Interest/Fee |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL intergration & posting will be done by FAST |  |  | To be confirmed | "Auto-Posting" definition for FAST to be done by Mazars
4.2 | Interest accruals
| - [Per loan] calculation for each loan contract (active & write-off) |  |  | Confirmed by TERASOFT
| - GL entry rule to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of loan : Principle/ Interest |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL posting for interests will be done by FAST |  |  | To be confirmed | "Auto-Posting" definition for FAST to be done by Mazars
4.3 | Related - fee
| - [Per loan] Detailed record for each type of fee (subject to Product Parameter)/ each contract |  |  | To be confirmed by Terasoft
| - GL entry rule to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of fee : Amount |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL posting for fees will be done by FAST |  |  | To be confirmed
4.4 | Repayments from clients (must be identified for each payment channel)
| - [Per loan] Detailed record for each client / each payment vendor |  |  | Confirmed by TERASOFT
| - Repayment hierachy is set-up under business rule to classify repayments to accurate GL |  |  | Confirmed by TERASOFT
| - GL entry rule to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - GL entry rule, based on hierachy, to be defined by MFI's accountant |  |  | To be confirmed
4.5 | Loan migration between buckets
| - [Per loan] Business rule in Terasoft to classify loan contracts |  |  | To be confirmed by Terasoft | 2.2 Loan provision'!A1
| - GL entry rule for "end of day" data to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of loan : Principle/ Interest/Fee |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL posting for interests will be done by FAST |  |  | To be confirmed | "Auto-Posting" definition for FAST to be done by Mazars
4.6 | Provisions
| - [Per loan] Business rule in Terasoft to classify loan contracts |  |  | To be confirmed by Terasoft | 2.2 Loan provision'!A1
| - GL entry rule for "end of day" data to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of loan : Principle/ Interest/Fee |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - Manual calculation for loan buckets will be done manually by Accountant or FAST |  |  | To be confirmed
| - GL posting for provisions will be done by Accountant or FAST |  |  | To be confirmed | Can be used by importing GL by FAST if "auto-posting" is not allowed
4.7 | Write-off for loan (bucket 5)
| - [Per loan] Business rule in Terasoft to classify loan contracts into "write-off" loans |  |  | To be confirmed by Terasoft | 2.2 Loan provision'!A1
| - GL entry rule for "end of day" data to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for each type of loan : Principle/ Interest/Fee |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL posting for loan buckets will be done manually by FAST |  |  | To be confirmed | "Auto-Posting" definition for FAST to be done by Mazars
4.8 | Revert of loan contracts
| - [Per loan] Business rule in Terasoft to classify loan contracts into "inactive" loans |  |  | To be confirmed by Terasoft | 2.3 Loan write-off'!A1
| (Including integration with Vendor's system such as MOMO, to identify "inactive" loans) |  |  | To be confirmed by Terasoft
| - GL entry rule for "end of day" data to be defined by MFI's accountant |  |  | To be confirmed by Terasoft
| - [Daily] Terasoft provide the summary information for "inactive loans" : Principle/ Interest/Fee |  |  | To be confirmed by Terasoft | "Intergration Data table" will be confirmed by MFI's accountant
| - GL posting for loan buckets will be done manually by FAST |  |  | To be confirmed | "Auto-Posting" definition for FAST to be done by Mazars
5/ | Intergration with FAST (subject to type of transactions in compliance with VAS) |  |  |  | "Intergration Data table" will be confirmed by MFI's accountant
| - Integration type : per loan/Customers |  |  | To be proposed by FAST/Mazars
| - Integration type : per End of Day |  |  | To be proposed by FAST/Mazars
6/ | Intergration with SBV Reporting |  |  |  | "Intergration Data table" will be confirmed by MFI's accountant
| - Integration type : per loan/Customers |  |  | To be proposed by SERENCO
| - Integration type : per End of Day |  |  | To be proposed by SERENCO
B/ | Business rule - Detailed Descriptions
# | Descriptions | Business Rule | Details | Status | Notes
1/ | Product description | Parameter |  | OK | See Product's parameter from SERGEY
2/ | Accounting policies
2.1 | Chart of account | Parameter (Data Table) | 1.1 COA_Terasoft'!A1 | OK
2.2 | Loan classification | Coding (By rule) | 2.2 Loan provision'!A1 | OK | Read 3.a
2.3 | Loan bucket & provision rate | Parameter (Data Table) | 2.2 Loan provision'!A1 | OK | Read 3.b
2.4 | Provision calculation | Coding (By rule) | 2.2 Loan provision'!A1 | OK | Read 3.d & e
2.5 | Loan write-off | Coding (By rule) | 2.3 Loan write-off'!A1 | OK
3/ | Collection/Disbursement channel | Coding (By rule) | 3.1 Payment Workflows'!A1 | OK
4/ | Accouting entry rule | Coding (By rule) | 1.4 Entry diagram'!A1 | To be revised by MFI's accountant under "1-1" accounting rule

## 1.1 COA (hidden)
<MICRO LOAN> Chart of Accounts
| Level 1 | Level 2 | GL name | Terasoft | Level 1 | Level 2 | GL name | Terasoft | Level 1 | Level 2 | GL name | Terasoft
| 1 |  | Current Assets |  | 4 |  | Liablility |  | 9 |  | Off-balance sheet items
|  | 10 | Cash on hand | N/A |  | 40 | Liability with SBV | N/A |  | 90 | _______________________ | N/A
|  | 11 | Deposits at SBV | N/A |  | 41 | Liability with other financial institutions | N/A |  | 91 | _______________________ | N/A
|  | 12 | Short-term Investments on government bonds | N/A |  | 42 | Customer's deposits | N/A |  | 92 | _______________________ | N/A
|  | 13 | Deposits at other financial institutions | Yes |  | 43 | Issuance of commercial papers | N/A |  | 93 | _______________________ | N/A
|  | 14 | Security | N/A |  | 44 | Entrusted funds | N/A |  | 94 | Interest & Fee receivable (Off-Balance sheet) | Yes
|  | 15 | Security avalable-for-sale | N/A |  | 45 | External payables | Yes |  | 95 | _______________________ | N/A
|  | 16 | Security held-to-maturity | N/A |  | 46 | Internal payables | N/A |  | 96 | _______________________ | N/A
|  | 17 | _______________________ | N/A |  | 47 | FX trading | N/A |  | 97 | Write-off debts (Off-balance sheet) | Yes
|  | 18 | _______________________ | N/A |  | 48 | Other liablility | N/A |  | 98 | _______________________ | N/A
|  | 19 | _______________________ | N/A |  | 49 | Interest & Fee paybables | Yes |  | 99 | _______________________ | N/A
[5 empty] | 5 |  | Bank Remittance | N/A
[5 empty] | 6 |  | Owner's Equity | N/A
| 2 |  | Loans to customers |  | 7 |  | Income
|  | 20 | Loans to other institutions | N/A |  | 70 | Income from loan activities | Yes
|  | 21 | Loans to domestic individuals & enterprises | Yes |  | 71 | Fees from service activities | N/A
|  | 22 | Purchase of commercial notes | N/A |  | 72 | Income from FX Activities | N/A
|  | 23 | Finance leasing | N/A |  | 73 | _______________________ | N/A
|  | 24 | Bank gurantee | N/A |  | 74 | Income from security trading | N/A
|  | 25 | Loans funded by untrusted funds | N/A |  | 75 | _______________________ | N/A
|  | 26 | Loans to foreign individuals & enterprises | N/A |  | 76 | _______________________ | N/A
|  | 27 | Other loans to domestic individuals & enterprises | N/A |  | 77 | _______________________ | N/A
|  | 28 | Debts awating for write-off | N/A |  | 78 | Profit from stock investments | N/A
|  | 29 | Other loans | N/A |  | 79 | Other income | N/A
| 3 |  | Fixed assets & other assets |  | 8 |  | Expense
|  | 30 | Fixed assets | N/A |  | 80 | Expense for loan activities | Yes
|  | 31 | Tools & other assets | N/A |  | 81 | Expense for service activities | N/A
|  | 32 | Purchase of assets | N/A |  | 82 | Expense for FX Activities | N/A
|  | 33 | _______________________ | N/A |  | 83 | Tax & Fees | N/A
|  | 34 | Long term investments | N/A |  | 84 | Expense for security trading | N/A
|  | 35 | External receivales | N/A |  | 85 | Personel cost | N/A
|  | 36 | Internal receivables | N/A |  | 86 | General administration expense | N/A
|  | 37 | _______________________ | N/A |  | 87 | Depreciation | N/A
|  | 38 | Other assets | N/A |  | 88 | Provision costs | Yes
|  | 39 | Interest & Fee receivables | Yes |  | 89 | Other expense | N/A

## 2.2 Loan provision
<Microloan> General regulations on "loan clasification & Provision"
1/ | Definitions
- | Debts classification is the division of loan principals into 5 groups ( 5 buckets)
- | Overdue debt is a debt where a part or the entire of its principal and /or interest has become overdue.
- | Bad debts (NPL) are debts, which have been classified loan group 3, 4 and 5 (as stated below)
- | Debts with restructured repayment term are debts, the repayment term of which MFI accepts to restructure or reschedule for customers
(but there are sufficient grounds for assessing that customers are capable to fully pay the principals and interests under the restructured repayment term
- | Specific provisions are an amount to be made available on the basis of the debts classification to provide against potential losses that may arise from each specific group of debts.
- | General provisions are an amount to be made available to provide against losses that have not yet been determinable during process of specific debts classification
2/ | Periodic debts classification and provisioning
a/ | For Internal management
- | Loan classification should be done on "AUTOMATICALLY/WEEKLY" basis on the "TERASOFT" for management purpose.
- | There will be "NO requirement" for accounting booking entry
b/ | For external reporting
- | Loan classification should be done on the "TERASOFT" for external reporting as follows:
|  | Loans outstanding | Date of completing loan classification | Date of posting GL entry
|  | + as of Mar 31 | By Apr 7 | By Apr 15
|  | + as of Jun 30 | By Jul 7 | By Jul 15
|  | + as of Sep 30 | By Oct 7 | By Oct 15
|  | + as of Nov 31 | By Dec 7 | By Dec 15
- | Based on the "auto"/"weekly" classification by TERASOFT, it is allowed for manual review and adjustments (if needed) for external reporting
3/ | Loan classification and setting up of specific provisions
a/ | Based on the due payment of the loan principal and interest, MFI shall classify the debts into five (05) groups as follows:
| Bucket | Loan status | Specific Provision rate ( r ) | Key criteria
| <1> | Active | 2% | Current debts; Normal Provision for loan loss
| <2> | Active | 10% | - Debts which are overdue for a period of 1 day to less than 30 days
- Debts with the repayment term to be restructured for one time.
| <3> | Active | 50% | Debts which are over due for a period of 30 to less than 60 days;
- Debts with the repayment term to be restructured for one time, which are overdue for less than 30 days under the restructured repayment period thereof;
- Debts, of which interests are exempted or reduced because customers are not capable of making full payment of interests under credit facility.
| <4> | Active | 75% | Debts, which are overdue for a period of 61 to less than 90 days;
Debts with the repayment term to be restructured for one time, which are overdue for a period of 61 to less than 90 days under the restructured repayment term thereof;
- Debts with the repayment term to be restructured for two times.
| <5> | Active | 100% | Debts, which are overdue for a period of 91 days and more;
- Debts with the repayment term to be restructured for one time, which are overdue for 90 days and more under the restructured repayment period thereof;
- Debts with the repayment term to be restructured for two times, which are overdue under that restructured repayment term;
- Debts with the repayment term to be restructured for three times and more, including those which have not yet been overdue or have been overdue;
| <5> | Write-off | 0% | - Debts which are approved to "write-off", but it is still needed to manage on our system for debt collections if any
| <5> | "Deleted" | 0% | - Debts which are approved to "write-off" after 5-years of "write-off)
| <1> | Inactive | 0% | - Debts which clients are not receiving the disbursements
b/ | Table of Loan buckets & 2 type of provision rate
|  | Bucket | Loan status | Specific Provision rate ( r ) | General provision rate ( r)
|  | <1> | Active | 2% | 2%
|  | <2> | Active | 10% | 2%
|  | <3> | Active | 50% | 2%
|  | <4> | Active | 75% | 2%
|  | <5> | Active | 100% | 0%
|  | <5> | Write-off | 0% | 0%
|  | <5> | "Deleted" | 0% | 0%
|  | <1> | Inactive | 0% | 0%
c/ | Specific policy for restructuring of loans's repayment term:
| 1/ | Customer need to send an application for a new loan
| 2/ | Re-assess the quality of customers which are qualified for MFI to re-structure the loan tenor
| 3/ | Being applied "free of charge" for application & service fee
| 4/ | Being disbursed "new loan" amount with the new loan tenor
| 5/ | New loan amount will be used for repayments
d/ | Specific Provision is calculated and booked in total amount as follows:
R = (A – C) x r
A: Outstanding principals of the debt
C: Deduction value of security asset. (it shall be "0" for MFI's microloan product which requires "no" deposit or security assets)
r: Provision rate
e/ | General provision is calculated and booked in total amount as
= 2% * [total value of outstanding debts from Group 1 to Group 4]
4/ | Business application procedure
| # | Tasks |  |  | Entity | Person - in - charge | Key documents | Notes
| 4.1 | Receives loan application from customer |  |  | LGC | Sales | Application form | By Terasoft
| 4.2 | Checks and verify the application |  |  | MCC | Verification |  | By Terasoft
| 4.3 | Confirms loan granting |  |  | MFI | Verification |  | By Terasoft
| 4.4 | Transfer MFI's Funds to Business Partners |  |  | MFI | Finance | *** Funding policy
| 4.5 | Disburses loan |  |  | MFI | Verification | Loan contract | By Terasoft
| 4.6 | Transfers service fee/application fee |  |  | MFI/LGC | Finance | Service contract | By ODOO
| 4.7 | GL Booking for loan/interest accruals/fee |  |  | MFI | Finance |  | By Terasoft + ODOO
| 4.8 | Reveives repayments (Loan/Interest…) - based on repayment hierachy |  |  | MFI | Collection | Partners' Business contract | By Terasoft
| 4.9 | GL Booking for repayments |  |  | MFI | Finance |  | By Terasoft + ODOO
| _4.10 | GL Reconciliation, including reconciliation with Payment/Collection Vendors |  |  | MFI | Finance
| _4.11 | Bank settlement with business partners (Collection/Payment Vendors) |  |  | MFI | Finance | Service contract | By ODOO
| _4.12 | Classify the loan into the right bucket on DAILY/WEEKLY basis (based on due date) |  |  | MFI | Credit risk | *** Loan provision policy | By Terasoft - Data extraction
| _4.13 | Classify the loan into the right bucket (Monthly) for external reporting |  |  | MFI | Credit risk | *** Loan provision policy | By Terasoft - Data extraction for user's calculation
| _4.14 | Calculate loan provision based on loan classification (Monthly) |  |  | MFI | Finance |  | By ODOO
| _4.15 | GL Booking for Loan Classification & Loan Provision |  |  | MFI | Finance |  | By ODOO
| _4.16 | FRD's reporting for Credit Provision |  |  | MFI | Finance

## 1.1 COA MFI & LGC
<ODOO> -Chart of Accounts
*** Genrenal definitions : 6 levels
| Level 1-2-3 : |  |  | 4 digits | Used for interegration with "GL - Accounting system"
| Level 4-5-6 : |  |  | 4 digits | Used for internal management
| Accounting/Intergration Purpose |  |  |  |  | Management Purpose
| Level 1 | Level 2 | GL Name | Level 3 | GL name | Level 4 | Level 5 | Level 6
[6 empty] | Sub-account | Currency code | Company
[6 empty] | 00 : default | 0 : Default as local currency | 0 : MFI
[6 empty] | xx : Subject to each GL | 1 : Foreign currency | x : LGC
| 1 digit |  |  | 2 digits |  | 1 digits | 1 digit | 2 digits (00 by default)
| 1 | 1 | Deposits at other financial institutions | 11 | Local currency - Current account | Bank/Funding/Collection/Partner | "0" | "0" & "x"
|  |  |  | 12 | Foreign currency - Current account | Bank/Funding/Collection/Partner | "1" | "0" & "x"
|  |  |  | 13 | Foreign Currency- Saving Account | Bank/Funding/Collection/Partner | "1" | "0" & "x"
| 1 | 2 | Cash In Hand | 21 | Local currency | Head Office/Branch/Transit | "0" | "0" & "x"
|  |  |  | 21 | Foreign Currency | Head Office/Branch/Transit | "1" | "0" & "x"
| 1 | 3 | Loans to domestic individuals & enterprises | 31 | Short-term Loan | 1 : Individuals/ 5 : Enterprises x : term (60 days/ 90 days/180 days/…) | "0" | "0"
|  |  |  | 32 | Short-term overdue Loan | x.x (Loan type + Term) | "0" | "0"
|  |  |  | 33 | Specific provision | Type of loan groups | "0" | "0"
|  |  |  | 34 | General provisions | 00 | "0" | "0"
| 1 | 4 | Interest & Fee receivables | 41 | Loan Interest accruals (receivables) | x.x (Loan type + Term) | "0" | "0"
|  |  |  | 42 | Loan-related Fee receivables | Type of fees | "0" | "x"
| 1 | 5 | Prepaid and Other recievable Assets | 51 | Prepaid and Advance | Different activites | "0" | "0" & "x"
|  |  |  | 52 | Other Receivables | Different activites | "0" | "0" & "x"
|  |  |  | 53 | Interelated Accounts | LGC/Mobile Money | "0" and "1" | "0" & "x"
| 1 | 6 | Tangible Assets | 61 | Fixed Assets | Different base on Assets | "0" | "0" & "x"
|  |  |  | 62 | Accumulated Depreciation of Assets | Different base on Assets | "0" | "0" & "x"
| 1 | 7 | Intangible and Other Non Current Assets | 71 | Intangibe Assets | Different base on Assets | "0" | "0" & "x"
|  |  |  | 72 | Amortizations | Different base on Assets | "0" | "0" & "x"
|  |  |  | 73 | Other Non Current Assets | Different base on Assets | "0" | "0" & "x"
| 2 | 1 | Loans from domestic and foreign | 11 | Loan from Banks | Loan type+Term and different banks | "0" and "1" | "0" & "x"
|  |  |  | 12 | Loan from Institutions | Loan type+Term and different institutions | "0" and "1" | "0" & "x"
| 2 | 2 | Deposits from the clients | 21 | Saving Deposits | Different Type of Savings | "0" | "0"
|  |  |  | 22 | Interest Payable on Saving Deposits | Different Type of Savings | "0" | "0"
| 2 | 3 | External payables | 31 | Income Tax Payable |  |  | "0" & "x"
|  |  |  | 32 | Salary Income Tax Payable |  |  | "0" & "x"
|  |  |  | 33 | Social, Security, Benefit Payable for staff |  | "0" or "1" | "0" & "x"
|  |  |  | 34 | Other Payables | Different activites | "0" or "1" | "0" & "x"
| 2 | 4 | Interest & Fee paybables | 41 | Loan-related Interest payables | Loan type+Term and different banks/Institutins | "0" or "1" | "0" & "x"
|  |  |  | 42 | Loan-related Fee payables | 00->09 : Type of fees | "0" | "x"
| 3 | 1 | Equity | 11 | Paid Up Capital |  | "0" | "0" & "x"
|  |  |  | 12 | Reserves | Different Type of Reserves | "0" | "0" & "x"
|  |  |  | 13 | Retained Earning | Up to date/ Prior / Current | "0" | "0" & "x"
| 4 | 1 | Income | 11 | Loan Interest income | Type of loan groups) | "0" | "0"
|  |  |  | 12 | Other income from loan activities | Type of fees | "0" | "x"
| 5 | 1 | Financial Expenses | 11 | Funding costs for depositors | Types of Savings | "0" | "0"
|  |  |  | 12 | Funding costs for lenders | Types of Loans | "0" or "1" | "0" & "x"
|  |  |  | 13 | Other costs for loan activities | Type of costs | "0" or "1" | "0" & "x"
| 6 | 1 | Provisions | 11 | Provision on loan loss | Types of Loans | "0" | "0"
|  |  |  | 12 | Other provision costs | Type of costs | "0" or "1" | "0" & "x"
| 6 | 2 | Write-off debts (Off-balance sheet) | 21 | Principle | Types of Loans | "0" | "0"
|  |  |  | 22 | Loan interest | Types of Loans | "0" | "0"
|  |  |  | 23 | Loan-related fee | Type of fees | "0" | "x"
| 6 | 3 | Expensses | 31 | Administrative Expenses | Types of Expenses | "0" or "1" | "0" & "x"
|  |  |  | 32 | Non-Operating Expenses | Types of Expenses | "0" or "1" | "0" & "x"
| 7 | 1 | Other Income | 11 | Loan Loss Recovery | Types of Loans | "0" | "0"
|  |  |  | 12 | Other Income | Types of Income | "0" | "0" & "x"

## 1.3 GL Intergration (hidden)
[Group] GL Intergration policy for key transactions
A. Financial transactions for intergrations |  | CRM : TERASOFT --> GL SYSTEM : FAST |  | Intergration PRIMARY key : GL CODE
# | Type of transaction | TERASOFT (Customer's detail) | FAST (Consolidated posting as total value) | Legal Entity | Intergration | Intergration time | Notes
1 | Loan disbursement to customer | Record each customer's loan grant --> MFI's Loan | Consolidated loans for all customers to MFI's accounting book | MFI | Yes | Per loan
2 | "Application fee" receivable from customer / Payable to LGC | Record/calculate each customer's fee when granting loan--> LGC's income | Consolidated fee/income for MFI/LGC's accounting book | MFI/LGC | Yes | Per loan
3 | "Service fee" receivable from customer/ Payable to LGC | Record/calculate each customer's fee when granting loan--> MCC's income | Consolidated fee/income for MFI/MCC's accounting book | MFI/LGC | Yes | Per loan
4 | Interest rate - "Daily" accrued | Record/calculate each customer' daily interest ---> MFI's income | Consolidated interest income for MFI's accounting book | MFI | Yes | End of day
5 | Overdue interest - "Daily" accrued | Record/calculate each customer' daily interest ---> MFI's income | Consolidated overdue interest income for MFI's accounting book | MFI | Yes | End of day
6 | Late payment fee - Accrued | Record each customer' interest ---> MFI's income | Consolidated late payment income for MFI's accounting book | MFI | Yes | End of day
7 | Repayments from customer for: | Deducted for each customer's type of debt in related to repayment hierachy | Consolidated deductions for all customers' each type of debt at MFI's accouting book
7.1 | Application fee | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.2 | Service fee | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.3 | Late payment fee | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.4 | Overdue interest accrued | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.5 | Interest accrued | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.6 | Prolongation fee | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
7.7 | Principle | Deducted for each customer's debt | Consolidated deduction for all customers | MFI | Yes | Per loan
8 | Loan migration between buckets | Reclassify and record each customer's loan | Consolidated data for all customers for posting to correct type of loans | MFI | Yes | End of day
9 | Provisions | Record/calculate each customer' type of loan and provision amount (specific provision & general provision) ---> MFI's provision expense | Consolidated each type of loan amount (among 5 types as current regulation) and corresponding loan provsions | MFI | Yes | End of day
10 | Write-off for loan (bucket 5) | Record each customer's debt write-off in accordance with the write-off legally business process | Consolidated write-off (Loan & Interest & Provision... reduction) for all customers to MFI's accounting book | MFI | Yes | End of day
B. Financial transactions posting on FAST only
1 | Service fee - Internal payments | NO | To be defined / Mazars | MFI/LGC…. | NO
2 | Funding transactions - Internal funding | NO | To be defined / Mazars | MFI/LGC…. | NO
3 | Payments for Operational cost / People cost | NO | To be defined / Mazars | MFI/LGC…. | NO
3.1 | Payments for Operational cost | NO | To be defined / Mazars | MFI/LGC…. | NO
3.2 | Payments for People cost - MFI | NO | To be defined / Mazars | MFI | Yes | HR Module & Finance Module | "Auto" GL Posting
3.3 | Payments for People cost - Other enterprises | NO | To be defined / Mazars | LGC…. | NO | HR Module & Finance Module | "Auto" Extracting to "GL template"
4 | Collection/Disbursements for business partners (Banks & Vendors) | NO | To be defined / Mazars | MFI/LGC…. | NO
5 | Month-end GL posting for financial reporting | NO | To be defined / Mazars | MFI/LGC…. | NO

## 1.4 Entry diagram (hidden)
<TERASOFT> Accounting Rule for double-entry
| Parameters | Entity
| Loan | MFI | 100 | $ |  | Total amount ($)
| Loan tenor |  | 30 | Days |  | 30 days | 20 days (Early payment)
| Service fee | MCC | 0.35% | per day |  | 10.5 | 10.5
| Service fee | LGC | 0.35% | per day |  | 10.5 | 10.5
| Interest | MFI | 0.3% | per day |  | 9 | 6
|  |  | 1% |  |  | 30 | 27
| Overdue interest |  | 0.45% | per day
| Late payment fee |  | 30 | $
Transaction type
| Transaction type |  | $ | Period |  |  | Transaction type |  |  | $ | Period
1 | Loan disbursement to customer |  | 100 | Per loan |  |  | 8 | Loan migration between buckets |  | 178
2 | "Application fee" receivable from customer / Payable to LGC |  | 10.5 | Per loan |  |  | 8.1 | Application fee |  | 10.5
3 | "Service fee" receivable from customer/ Payable to LGC |  | 10.5 | Per loan |  |  | 8.2 | Service fee |  | 10.5
4 | Interest rate - "Daily" accrued |  | 0.3 | Per day |  |  | 8.3 | Late payment fee |  | 30
5 | Overdue interest - "Daily" accrued |  | 0.45 | Per day |  |  | 8.4 | Overdue interest accrued |  | 18
6 | Late payment fee - Accrued |  | 30 | Per loan |  |  | 8.5 | Interest accrued |  | 9
[7 empty] | 8.6 | Prolongation fee |  | 0
7.a | Early Repayments from customers for loans by "Due date" |  | 127 |  |  |  | 8.7 | Principle |  | 100
7.1 | Application fee |  | 10.5 |  |  |  | 9 | Provisions
7.2 | Service fee |  | 10.5 |  |  |  | 9.1 | General provision
7.3 | Late payment fee |  | 0 |  |  |  | 9.2 | Specific provision
7.4 | Overdue interest accrued |  | 0 |  |  |  | 10 | Write-off for loan (bucket 5) |  | 178
7.5 | Interest accrued |  | 6 | Per day * 20 days |  |  | 10.1 | Application fee |  | 10.5
7.6 | Prolongation fee |  | 0 |  |  |  | 10.2 | Service fee |  | 10.5
7.7 | Principle |  | 100 | FULL repaid |  |  | 10.3 | Late payment fee |  | 30
7.b | Repayments from customers for loans (Bucket 1) |  | 160 |  |  |  | 10.4 | Overdue interest accrued |  | 18
7.1 | Application fee |  | 10.5 |  |  |  | 10.5 | Interest accrued |  | 9
7.2 | Service fee |  | 10.5 |  |  |  | 10.6 | Prolongation fee |  | 0
7.3 | Late payment fee |  | 30 | subject to overdue days |  |  | 10.7 | Principle |  | 100
7.4 | Overdue interest accrued |  | 4.05 | 9 days of overdue
7.5 | Interest accrued |  | 9
7.6 | Prolongation fee |  | 0
7.7 | Principle |  | 95.95 | Partially repaid
7c. | Repayments from customers for overdue loans (Bucket 2) |  | 160
7.1 | Application fee |  | 10.5
7.2 | Service fee |  | 10.5
7.3 | Late payment fee |  | 30
7.4 | Overdue interest accrued |  | 9 | Per day * 20 days
7.5 | Interest accrued |  | 9 | Per day * 30 days
7.6 | Prolongation fee |  | 0
7.7 | Principle |  | 91 | Partially repaid
7d. | Repayments from customers for overdue loans (Bucket 3-4-5) |  | 175
7.1 | Application fee |  | 10.5
7.2 | Service fee |  | 10.5
7.3 | Late payment fee |  | 30
7.4 | Overdue interest accrued |  | 18 | Per day * 40 days
7.5 | Interest accrued |  | 9 | Per day * 30 days
7.6 | Prolongation fee |  | 0
7.7 | Principle |  | 97 | Partially repaid
Accounting rule |  | Must have | Must have | Must have | Must have | Optional | Optional | Optional | Optional | Optional
# | Transaction type / description | Date | GL code | Debit amount | Credit amount | Currency | GL name | Legal entity | Notes for "TERASOFT" applications | Notes for "FAST" intergrations (to be confirmed)
1 | Loan disbursement to customer
1.a | Loan fundings to MOMO accounts for loan disbursements
|  | D-1 | 13114100 | 500 |  | #REF! | #REF! | #REF!
|  | D-1 | 13110100 |  | 500 | #REF! | #REF! | #REF! | TERASOFT should be integrated with MOMO to post this transaction "auto"
1.b | Loans disbursement to customer by "MOMO" payment gateway
|  | D | 21111100 | 100 |  | #REF! | #REF! | #REF!
|  | D | 13114100 |  | 100 | #REF! | #REF! | #REF! | For each payment vendors, TERASOFT shall have each separate GL code
1.c | Repayments from MOMO accounts to funding account
|  | D | 13110100 | 300 |  | #REF! | #REF! | #REF!
|  | D | 13114100 |  | 300 | #REF! | #REF! | #REF! | TERASOFT should be integrated with MOMO to post this transaction "auto"
1.d | Transactional cost for loan disbursements (Paid to MOMO) | D | 80900200 | 1 |  | #REF! | #REF! | #REF!
|  | D | 13110100 |  | 1 | #REF! | #REF! | #REF! | No need to do on TERASOFT | Will be done manually on FAST
2 | "Application fee" receivable from customer / Payable to LGC
|  | D | 39702101 | 10.5 |  | #REF! | #REF! | #REF! | TERASOFT should record for each transaction/ each customer | Shall be defined 2 seperate entries between LGC & MFI
|  | D | 70902001 |  | 9.5455 | #REF! | #REF! | #REF!
|  | D | 45310101 |  | 0.95455 | #REF! | #REF! | #REF!
3 | "Service fee" receivable from customer/ Payable to LGC
|  | D | 39702102 | 10.5 |  | #REF! | #REF! | #REF! | TERASOFT should record for each transaction/ each customer | Shall be defined 2 seperate entries between MCC & MFI
|  | D | 70902001 |  | 9.5455 | #REF! | #REF! | #REF!
|  | D | 45310101 |  | 0.95455 | #REF! | #REF! | #REF!
4 | Interest accruals for standard loans
4.a | Daily interest accruals
|  | D+1 | 39411100 | 0.3 |  | #REF! | #REF! | #REF!
|  | D+1 | 70201100 |  | 0.3 | #REF! | #REF! | #REF! | Interest could be calculated for each loan contract, and posting 1 entry by the "total interest amount" at end of the day
4.b | Daily interest accruals
|  | D+2 | 39411100 | 0.3 |  | #REF! | #REF! | #REF!
|  | D+2 | 70201100 |  | 0.3 | #REF! | #REF! | #REF! | Interest could be calculated for each loan contract, and posting 1 entry by the "total interest amount" at end of the day
5 | "DAILY" Interest accruals for over due loans
5.a | [Loan under BUCKET 1] Within the grace period (2 days) | D + 31 | [6 empty] | No GL booking during the grace period
|  | D + 32 | [6 empty] | No GL booking during the grace period
5.b | [Loan under BUCKET 1] The 1st day after grace period
|  | D + 33 | 39411100 | 1.35 |  | #REF! | #REF! | #REF! | Interest could be calculated for 3 days (including 2 days of grace period) for each loan contractand posting 1 entry by the "total interest amount" at end of the day
|  | D + 33 | 70201100 |  | 1.35 | #REF! | #REF! | #REF!
5.c | [Loan under BUCKET 1] The 2nd day after grace period
|  | D + 34 | 39411100 | 0.45 |  | #REF! | #REF! | #REF! | Interest could be calculated for 1 day for each loan contract, and posting 1 entry by the "total interest amount" at end of the day
|  | D + 34 | 70201100 |  | 0.45 | #REF! | #REF! | #REF!
5.d | [Loan under BUCKET 2--> 5] The 2nd day after grace period
|  | D + 40 | 39411200 | 0.675 |  | #REF! | #REF! | #REF!
| Bucket 1-- > Bucket 2 | D + 40 | 70201200 |  | 0.675 | #REF! | #REF! | #REF!
|  | D+60 | 39411300 | 0.675 |  | #REF! | #REF! | #REF!
| Bucket 2-- > Bucket 3 | D+60 | 70201300 |  | 0.675 | #REF! | #REF! | #REF!
|  | D+120 | 39411400 | 0.675 |  | #REF! | #REF! | #REF!
| Bucket 3-- > Bucket 4 | D+120 | 70201400 |  | 0.675 | #REF! | #REF! | #REF!
|  | D+210 | 39411500 | 0.675 |  | #REF! | #REF! | #REF!
| Bucket 4-- > Bucket 5 | D+210 | 70201500 |  | 0.675 | #REF! | #REF! | #REF!
6 | Late payment fee - Accrued
(When MFI receives the late payment fee for overdue loans)
|  | D + 39 | 39701200 | 30 |  | #REF! | #REF! | #REF! | Late payment fee is recored by each loan contract, and posting this entry by the "total amount" at end of the day
|  | D + 39 | 70901000 |  | 30 | #REF! | #REF! | #REF!
7 | Repayments from customers
7.a | Early Repayments from customers for loans by "Due date"
Bucket 1 | Total receipt from customers through MOMO account | D + 20 | 13117100 | 127 |  | #REF! | #REF! | #REF! | TERASOFT should be integrated with MOMO to post this transaction "auto"
| Application fee | D + 20 | 39702101 |  | 10.5 | #REF! | #REF! | #REF! | Payments should be deducted in according to "payment hierachy" which should be defined by the system. TERASOFT will divide the cashflows to reflect many entries by "1-1" rule
| Service fee | D + 20 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 20 | 39701100 |  | 0 | #REF! | #REF! | #REF!
| Interest accrued | D + 20 | 39411100 |  | 6 | #REF! | #REF! | #REF!
| Prolongation fee | D + 20 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 20 | 21910100 |  | 100 | #REF! | #REF! | #REF!
7.b | Repayments from customers for loans (Bucket 1)
Bucket 1 | Total receipt from customers through MOMO account | D + 39 | 13117100 | 160 |  | #REF! | #REF! | #REF! | TERASOFT should be integrated with MOMO to post this transaction "auto"
| Application fee | D + 39 | 39702101 |  | 10.5 | #REF! | #REF! | #REF! | Payments should be deducted in according to "payment hierachy" which should be defined by the system
| Service fee | D + 39 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 39 | 39701200 |  | 30 | #REF! | #REF! | #REF!
|  | D + 39 |  |  | 4.05 | #REF!
| Interest accrued | D + 39 | 39411100 |  | 9 | #REF! | #REF! | #REF!
| Prolongation fee | D + 39 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 39 | 21910100 |  | 95.95 | #REF! | #REF! | #REF!
7c. | Repayments from customers for overdue loans (Bucket 2)
Bucket 2 | Total receipt from customers through MOMO account | D + 50 | 13117100 | 160 |  | #REF! | #REF! | #REF!
| Application fee | D + 50 | 39702101 |  | 10.5 | #REF! | #REF! | #REF!
| Service fee | D + 50 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 50 | 39701200 |  | 30 | #REF! | #REF! | #REF!
| Overdue interest accrued | D + 50 | 39411200 |  | 9 | #REF! | #REF! | #REF!
| Interest accrued | D + 50 | 39411200 |  | 9 | #REF! | #REF! | #REF!
| Prolongation fee | D + 50 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 50 | 21121200 |  | 91 | #REF! | #REF! | #REF!
7d. | Repayments from customers for overdue loans (Bucket 3-4-5)
Bucket 3 | Total receipt from customers through MOMO account | D + 70 | 13117100 | 175 |  | #REF! | #REF! | #REF!
| Application fee | D + 70 | 39702101 |  | 10.5 | #REF! | #REF! | #REF!
| Service fee | D + 70 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 70 | 39701200 |  | 30 | #REF! | #REF! | #REF!
| Overdue interest accrued | D + 70 | 39411300 |  | 18 |  | #REF! | #REF!
| Interest accrued | D + 70 | 39411300 |  | 9 | #REF! | #REF! | #REF!
| Prolongation fee | D + 70 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 70 | 21121300 |  | 97 | #REF! | #REF! | #REF!
Bucket 4 | Total receipt from customers through MOMO account | D + 120 | 13117100 | 175 |  | #REF! | #REF! | #REF!
| Application fee | D + 120 | 39702101 |  | 10.5 | #REF! | #REF! | #REF!
| Service fee | D + 120 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 120 | 39701200 |  | 30 | #REF! | #REF! | #REF!
| Overdue interest accrued | D + 120 | 39411400 |  | 18 | #REF! | #REF! | #REF!
| Interest accrued | D + 120 | 39411400 |  | 40.5 | #REF! | #REF! | #REF!
| Prolongation fee | D + 120 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 120 | 21121400 |  | 65.5 | #REF! | #REF! | #REF!
Bucket 5 | Total receipt from customers through MOMO account | D + 210 | 13117100 | 175 |  | #REF! | #REF! | #REF!
| Application fee | D + 210 | 39702101 |  | 10.5 | #REF! | #REF! | #REF!
| Service fee | D + 210 | 39702102 |  | 10.5 | #REF! | #REF! | #REF!
| Late payment fee | D + 210 | 39701200 |  | 30 | #REF! | #REF! | #REF!
| Overdue interest accrued | D + 210 | 39411500 |  | 81 | #REF! | #REF! | #REF!
| Interest accrued | D + 210 | 39411500 |  | 40.5 | #REF! | #REF! | #REF!
| Prolongation fee | D + 210 | 39701300 |  | 0 | #REF! | #REF! | #REF!
| Principle | D + 210 | 21121500 |  | 2.5 | #REF! | #REF! | #REF!
8 | Loan migration between buckets
8.a | Loan migration from bucket 1 --> bucket 2/3/4/5
| *** Bucket 1 --> 2 | D + 40 | 21121200 | 100 |  | #REF! | #REF! | #REF!
|  | D + 40 | 21111100 |  | 100 | #REF! | #REF! | #REF!
|  | D + 40 | 39411200 | 13.5 |  | #REF! | #REF! | #REF!
| ( GL Posting at the migration date) | D + 40 | 39411100 |  | 13.5 | #REF! | #REF! | #REF!
|  | D + 40 | 80900100 | 13.5 |  | #REF! | #REF! | #REF!
|  | D + 40 | 70201200 |  | 13.5 | #REF! | #REF! | #REF!
| *** Bucket 2 --> 3 | D + 60 | 21121300 | 100 |  | #REF! | #REF! | #REF!
|  | D + 60 | 21121200 |  | 100 | #REF! | #REF! | #REF!
| ( GL Posting at the migration date) | D + 60 | 39411300 | 22.5 |  | #REF! | #REF! | #REF!
|  | D + 60 | 39411200 |  | 22.5 | #REF! | #REF! | #REF!
|  | D + 60 | 80900100 | 22.5 |  | #REF! | #REF! | #REF!
|  | D + 60 | 70201300 |  | 22.5 | #REF! | #REF! | #REF!
| *** Bucket 3 --> 4 | D + 120 | 21121400 | 100 |  | #REF! | #REF! | #REF!
|  | D + 120 | 21121300 |  | 100 | #REF! | #REF! | #REF!
| ( GL Posting at the migration date) | D + 120 | 39411400 | 49.5 |  | #REF! | #REF! | #REF!
|  | D + 120 | 39411300 |  | 49.5 | #REF! | #REF! | #REF!
|  | D + 120 | 80900100 | 49.5 |  | #REF! | #REF! | #REF!
|  | D + 120 | 70201400 |  | 49.5 | #REF! | #REF! | #REF!
| *** Bucket 4 --> 5 | D + 210 | 21121500 | 100 |  | #REF! | #REF! | #REF!
|  | D + 210 | 21121400 |  | 100 | #REF! | #REF! | #REF!
| ( GL Posting at the migration date) | D + 210 | 39411500 | 90 |  | #REF! | #REF! | #REF!
|  | D + 210 | 39411400 |  | 90 | #REF! | #REF! | #REF!
|  | D + 210 | 80900100 | 90 |  | #REF! | #REF! | #REF!
|  | D + 210 | 70201500 |  | 90 | #REF! | #REF! | #REF!
9 | Provisions
9.1 | General provision | [7 empty] | TERASOFT will provide the data | GL will be done on FAST
9.2 | Specific provision | [7 empty] | TERASOFT will provide the data | GL will be done on FAST
10 | Write-off for loan (bucket 5)
Application fee
Service fee
Late payment fee
Overdue interest accrued
Interest accrued
Prolongation fee
Principle

## 1.5 Cost Center (hidden)
<MFI> Cost Centers policy
1/ | General regulations
- | Cost centers is set at departmental level
- | Cost centers for transactions in FAST : Used the list below for setting up into the "FAST" finance module
+ | Each financial transactions/GL booking must be charged to specific cost centers (for budget verification & control)
+ | For payment module : Each payments must be charged to each cost center
+ | For procurement & asset functions : Assets must be recored for each cost centers, and the depreciation will be charged accordingly
+ | For HR Module : Personnel cost must be "auto" charged
- | Cost center for transactions intergrated between "FAST" and "TERASOFT" : Default as "22" (Direct sale)
2/ | List of cost centers
| No. | Code | Full name
| 1 | 00 | Regional Management Team
| 2 | 10 | Local Management Team
| 3 | 20 | Legal & Comliance
| 4 | 21 | Audit
| 5 | 22 | Direct sales
| 6 | 23 | Bank
| 7 | 24 | Marketing
| 8 | 25 | QA
| 9 | 26 | Accounting
| 10 | 27 | Treasury
| 11 | 28 | IT
| 12 | 29 | Operations
| 13 | 30 | Office admin
| 14 | 31 | Project Team
| 15 | 32 | Credit risk
| 16 | 33 | Operational risk
| 17 | 34 | HR
| 18 | 35 | TBC
| 19 | 36 | TBC
| 20 | 37 | TBC
| 21 | 38 | TBC
| 22 | 39 | TBC
| 23 | 40 | TBC

## 2.1 Product Parameters (hidden)
<Microloan> product parameters
# | Parameter | Value | Comments
1 | Type of loan | Cash microloan, repayment of which should be done by 1 payment at the end of the loan tenor | OK
2 | Loan amount | 1-30M VND | OK
3 | Loan tenor | 7-60 calendar days | OK
4 | Repayment schedule | Consists of 1 payment, enough to cover full debt. | OK
5 | Interest rate | 0,3% per each day of the loan tenor. Interest is calculated every day during the loan tenor, starting from the date of disbursement. Interest due date is the PAY DAY. Interest can be repaid earlier than the PAY DAY, but not earlier than early loan repayment conditions will be fully met. Interest is repaid online, and partial repayment is allowed in accordance to repayment hierarchy | Already revised
6 | Early loan repayment | Allowed, after at least half of loan tenor will pass, but not earlier than 7 calendar days | OK
7 | Early loan repayment fee | 0k VND | OK
8 | Overdue interest rate | 0,45% per each day Overdue interest is calculated every day after the loan tenor (including grace period) is passed and the loan amount is not fully repaid. Overdue Interest is repaid online, and partial repayment is allowed in accordance to repayment hierarchy | Already revised
9 | Late payment fee | 600K VND One-time fee, charged in case the customer haven't fully repaid loan amount after the loan tenor (including grace period) is finished. First time the fee is charged on the day (equally PAY DAY + GRACE PERIOD). Further fee is charged on the same day next month in case the customer have not fully repaid the loan amount. Fee is repaid online after receiving customer's payment. Partial repayment is allowed | Already revised
10 | Late payment fee grace sum | 50k VND In case customer's overdue loan is less than this amount, overdue interest rate and late payment fee are not charged | OK
11 | Late payment fee grace period | 2 working days | OK
12 | Loan prolongation fee | Existing loan prolongation service for another 30 calendar days …………. | OK
13 | Repayment hierarchy | 1. Application fee 2. Service fee 3. Late payment fee 4. Overdue Interest accrued 5. Interest accrued 6. Prolongation fee 7. Principle 8. Other fees | Already revised
14 | Initial loan sales business process |  | OK
15 | Repeat loan sales business process |  | OK
16 | Online application form |  | OK
17 | Customer support business processes |  | OK
18 | Application form |  | OK
19 | Provisions | Provision includes the following 5 types : …………. | 5 type of buckets should be defined in CRM for migration of loans every month
20 | Loans wright-off | Loans wright - off is done provisions formed in case the following conditions are met: 1. Appropriate loan is officially considered as bad 2. Appropriate loan's provision rate is 100% | Should be checked with for business procedure
New proposals
21 | Application fee (@LGC) | 0,35% per each day for the full loan tenor (non-refundable in case of early payment). Deducted to loan amount when disbursement, and received from customer at the PAY DAY | Used for posting entry between MFI & LGC, and payment tracking with customers
22 | Service fee (@ MCC) | 0,35% per each day for the full loan tenor (non-refundable in case of early payment). Deducted to loan amount when disbursement, and received from customer at the PAY DAY | Used for posting entry between MFI & MCC, and payment tracking with customers
23 | Date of application completing | Captured from online-application (sent to CRM) | Used for tracking with Online - system
24 | Date of loan grant | The day when MFI grants PDL to customer. | Used for prediction of funds needed
25 | Date of loan disbursement | The day when MFI completely transfers the loan amount to customer's bank account. It should be the starting date of the loan tenor, and used for daily interest calculation | Used for calculation of interest accrued
26 | Pay day (Date of repayment) | The day when customer repays the full debt (all loan and interests). It is defined by date of disbursement plus customer's specific loan tenor | Used for prediction of cash flows

## 2.3 Loan write-off
<Microloan> General regulations on "Loan revert & Loan write-off"
1/ | Definitions
- | This policy is going to be apply for :
+ | Revert of loan contracts : All outstanding debts (Principle/Interest/Fee) are going to revert
+ | Write-off of loan contracts: All outstanding debts (Principle/Interest/Fee) are going to write-off
2/ | Revert of loan contract
a. | Applicable conditions:
- | MFI is allowed to revert of loans for debts in following cases:
+ Customer is not going to receive loan disbursements after a specific number of days (by default of 4 days); and
+ MFI decide to cease the contract before the loan tenor is ended.
(This article should be included in the loan contract)
b. | Business procedure
# | Tasks |  | Entity | Person - in - charge | Key documents | Notes
2.1 | MFI disburses loan (through MOMO) |  | MFI | Verification |  | By Terasoft
2.2 | MFI record loan contract and calculation of interest and applicable fees |  | MFI | Finance |  | By Terasoft
2.3 | MFI (Sale) will contact the clients (who do not receive disbursement after 2 days) for reminder |  | MFI | Sale
2.4 | MFI (TERASOFT) will classify as "terminated contracts" (inactive contract) |  | MFI | Finance |  | By Terasoft
2.5 | MFI will post a revert entry of loan/interest to MFI's book |  | MFI | Finance |  | By ODOO
2.6 | MFI will post a entry of fee (payable to LGC) as MFI's operational cost |  | MFI | Finance |  | By ODOO
3/ | Write-off of loan contract
a. | Applicable conditions:
- | MFI is allowed to use credit provisions to deal with the credit risks for debts in following cases:
+ Debts classified to the Group 5; or
+ Customers are individuals who die or are missing or are disabled permanently and have no labor capacity to conduct income generation activities.
- | MFI is dealing with credit risks shall be made on the basis of following principles:
+ Firstly, the specific provisions is used to deal with credit risks for that debt
+ Secondly, the general provisions can be used for the full settlement
+ After speficic & general provision are used, MFI is allowed to directly charge the deficient amount to the operational expenses or revert excessive provison to the accounting income
+ MFI's staffs and related individuals shall not be permitted to inform customer of the settlement of the credit risks in any form
+ After provisions have been used to deal with the credit risks, MFI shall transfer the debts from the on-balance sheet accounts to the off-balance sheet accounts for continuously following-up
+ For the debts which have been transferred to the off-balance sheet accounts, MFI shall charge them to the incomes of the accounting period when collected;
+ After 5 years from the use of provisions and having taken all measures for the debts recovery, MFI shall be entitled to release the settled debts from the off-balance sheets accounts
- | MFI must organize a "Risk Settlement Committee", which is consisting of:
+ Chairman of the Board of Directors, or authorized person, to be as Chairman of this committee;
+ Funtional members: Head of Controllers Committee, Chief of Accounting Division, Chief of Credit Division;
+ Other optional members, which are decided by the Chairman.
- | Responsibility of the Risk Settlement Committee
a) To review the debts classification, setting up of provisions against credit risks, which have been performed by CEO
b) To decide the use of provisions to deal with credit risks.
c) To decide the plan of the debt recovery for the debts that have been dealt with, in which the time and applicable measures for the debt recovery must be identified.
d) To follow up the performance of the debts recovery for the debts that have been used provisions to deal with credit risks.
b. | Business procedure
# | Tasks |  | Entity | Person - in - charge | Key documents | Notes
3.1 | MFI must organize a "Risk Settlement Committee" |  | MFI | Credit Risk
3.2 | Review on bad debts (List of bad debts are printed out from TERASOFT) |  | MFI | Credit Committee | *** Write-off policy
3.3 | Make the final "loan write-off" decision |  | MFI | Credit Committee | *** Write-off policy
3.4 | Classify contract status ("Write-off" contract) among TERASOFT |  | MFI | Credit risk | *** Write-off policy | By Terasoft
3.5 | GL Posting for "Write-off" loans |  | MFI | Finance | *** Write-off policy | By ODOO
3.6 | Collection procedure for write-off loans |  | MFI | Collection | *** Write-off policy | By Terasoft
3.7 | GL Posting for "Collected" loans |  | MFI | Finance | *** Write-off policy | By ODOO
3.8 | Classify contract status ("Deleted" contract) |  | MFI | Credit risk | *** Write-off policy | By Terasoft
3.9 | GL Posting for "Deleted" loans |  | MFI | Finance | *** Write-off policy | By ODOO

## 3.1 Payment Workflows
[MFI] Business Workflows & GL Reconcilation for business partners
A/ | MMM
1/ | Business workflows - Disbursements |  | Date | Duration | Terasoft | Notes | Status
| 1.1 | MFI will create bank account | D-1 |  |  | This bank is at the same bank with MMM
| 1.2 | MMM will create a "MMM AGENT" account | D-1 |  |  | This bank account is used for MFI's transactions : Funding/Disbursements.
| 1.3 | MFI will do Funding transaction (Through Online-Banking) to this account | D-1 |  | x | - MFI's accoutant will do it on the daily/weekly basis ("D-1" day for disbursements on "D" day) - [MFI] Terasoft will have the "GL" code for each vendor for reconcilation
| 1.4 | MFI will create/send the data of disbursements on "D" day | D |  | x | - [MFI - MMM Data intergration] : {Full name/ Contract No/ Client's ID/ Client's mobile phone/ Amount/ Date & Time} - [MFI] TERASOFT will intergate these kind of information with MMM's system - [MFI] TERASOFT should have a report for tracking the disbursement transactions with MMM for fee's weekly/ monthly reconcilation
| 1.5 | MMM will perform the disburments (in full amount), and inform clients by MMM app or SMS (OTP). |  |  |  | Fees is paid by MFI
|  | - By MOMO's shop for cash-out | D |  |  | - 25k per transaction (1mil - 5mil)
|  | - By MOMO - Ewallet | D |  |  | - 1% + 1.5k per transaction (1mil - 5mil)
|  | - By MMM (Including direct cash-out at MMM shop for clients who do not have the MMM App) | D | To be confirmed |  | - 5k + (3.3k/time if Client use MOMO Ewallet to transfer to their bank, or 8k-12k/time if client receives cash at MMM shops)
|  | - By MMM (Including direct cash-out at MMM shop for clients who do not have the MMM App) | D | To be confirmed |  | - SMS fee MMM pays for SMS service provider if clients are not going to receive the disbursement
| 1.6 | Clients will receive the disbursement in 2 ways:
|  | - Use the MMM App to transfer money to Client's bank account | D --> D+2 | To be confirmed |  | Clients must install MMM - Apps in their smartphone
|  | - Come to MMM's shop to receive the loans | D --> D+2 | To be confirmed |  | Clients must show the ID, "OTP" code, and sign-off the receiving form (MMM keeps this form as evidence of cash-out).
| 1.7 | MMM will inform MFI about the success of disbursement | D |  | x | [MFI] TERASOFT will intergate these kind of information with MMM's system
| 1.8 | MMM deduct MFI's "MMM AGENT" account | D |  | x
| 1.9 | MFI (Sale) will contact the clients (who do not receive disbursement after 2 days) for reminder | D+2 --> D+4
| _1.10 | MMM will cease the loan in their system for the "pending disbursement list" (who do not receive disbursement after 4 days) | D+4 |  |  | To be confirmed by MMM
| _1.11 | MFI (TERASOFT) will classify the contract as "terminated" contracts for next steps | D+4 |  | x | This disbursement (including LGC's fee) can be considered to revert/write-off to MFI's book (Official procedure should be released)
| _1.12 | MMM & MFI will do the reconcilation on the "weekly/monthly" basis | EOM + 2D |  |  | MFI's accountant will manually do it (Based on MMM's report & Terasoft's report)
| _1.13 | MFI will confirm and pay the fee to MMM's account | EOM + 7D |  |  | MFI's accountant will manually do it. The payment should be credited to MMM'S another bank account
2/ | Business workflows - Collection |  | Date | Duration | Terasoft | Notes | Status
| 2.1 | MFI will create bank account. | >= D-1 |  |  | This bank should be at the same bank with MMM
| 2.2 | MMM will create a "MMM AGENT" account | >= D-1 |  |  | This bank account is used for MFI's transactions : Funding/Disbursements.
| 2.3 | MFI will create and transfer "repayment" notification/reminder to clients | >= D-1 |  | x | Done by MFI (TERASOFT to be intergrated with SMS service providers)
| 2.4 | Clients will process the repayments in 2 ways: |  |  |  | Fees will be paid by Clients
|  | - Come to MMM's shop | D | To be confirmed |  | - 1% + 1.5k per transaction (1mil - 5mil)
|  | - Use MMM - Ewallet | D | To be confirmed |  | - 1% + 1.5k per transaction (1mil - 5mil)
- Fee sharing : 1.0% + 1.5k per transaction (1mil - 5mil) to MMM, + 0.5% will be returned to MFI
| 2.5 | MMM will process the collection, and client wil get collection confirmation (By MMM Apps or SMS) | D | To be confirmed
| 2.6 | MMM will inform MFI about the success of repayment | D | To be confirmed | x | - [MFI - MMM data intergration] : {Contract No/ Client's ID/ Amount/ Date & Time} - [MFI] TERASOFT will intergate these kind of information with MMM's system
| 2.7 | MMM will transfer to MFI's "MMM AGENT" account for collection of repayments in "D" day | D | To be confirmed | x
| 2.8 | MFI can transfer the repayments from "MMM AGENT" account to MFI's Bank account | D+1 |  | x | MFI's accountant will manually do it
| 2.9 | MMM & MFI will do the reconcilation on the "monthly" basis | EOM + 5D |  |  | MFI's accountant will manually do it (Based on MMM's report & Terasoft's report)
| _2.10 | MFI will confirm and pay the fee to MMM's account | EOM + 7D |  |  | MFI's accountant will manually do it. The payment should be credited to MMM'S another bank account
3/ | Data integration between MFI & MMM |  | Date |  | Terasoft | Notes | Status
| 3.1 | Client's data for disbursement process |  |  | x | ONE-WAY : [MFI must send to MMM]
- Full name
- Contract Number
- Client's ID number
- Client's mobile phone number
- Total amount
- Date of transaction
- Time of transaction
| 3.2 | Client's data for collection process |  |  | x | ONE-WAY : [MMM must send to MFI]
|  | - Contract Number |  |  |  | Should be unique
|  | - Client's ID number |  |  |  | Should be unique
- Total amount
- Date of transaction
- Time of transaction
4/ | Business relations |  | Date |  |  | Notes | Status
| 3.1 | MOU will be signed within MAY/2015 | 2015-05-28
| 3.2 | Technical connection & testing | TBC |  |  | After MOU - sign off
| 3.3 | Official contract will be signed when MFI have the license | TBC
B/ | VN POST
| Business relations |  | Date |  |  | Notes | Status
| 3.1 | MOU will be signed | 2015-06-01 |  |  | Discussing with VN POST for MOU
| 3.2 | Technical discussion will be done | TBC |  |  | After MOU - sign off
| 3.3 | Official contract will be signed when MFI have the license | TBC
C/ | BANKS
| Business relations |  | Date |  |  | Notes | Status
| 1/ | Collection channel with local commercial baks shall be considered later |  |  |  | Clients will transfer/deposit the repayments to our bank accounts | Agreed with Sergey
| 2/ | Key concern points :
|  | - Intergration |  |  |  | TERASOFT or Back-end system with Bank's corebanking should be done. We can not control the client's financial information munually | Agreed with Sergey

## 4.1 Tax
<Each Company> TAX Reporting
1/ | General information
- | Tax reports are to be used IRD Format if IRD announce to use their format by non LTP companies. If not, use the Financial Report which is printed by Odoo and audited.
2/ | List of reports
| Reported to | Type of information | Applied for |  | Frequency | System | Person in charge | Notes | Ref
| Tax | Income Tax | MFI | x | Current Situation only yearly but IRD | Odoo | Financial Manager
|  | Financial Report | LGC | x | is trying to be quarterly and also yearly
| Tax | Income Tax | MFI | x | To be informed to Township IRD by Quarterly | HR System (Payroll Calculation) | HR Manager | We need to prepare staff list and income tax on salaries of each staff. This tax need to be calculated at each month together with payroll.
|  | Employees' salaries | LGC | x
| Tax | Commercial Tax | LGC | x | To be informed to Township IRD by Quarterly | Odoo | Financial Manager
Service Fees of LGC

## 4.2 FRD
<Loan> Regulator Reporting
1/ | General information
- | Odoo will support the Financial Report which is customized FRD format.
- | Terasoft need to support related with Progress Reports. And need to check with Terasoft for FRD Format.
- | Need to check the rules and reguslations for LGC according to its businees to know which minister will be regulator for it.
- | Base on regulator of LGC, need to prepare the reports.
2/ | List of reports
| Reported to | Type of information | Regulations |  | Time to send | Applied for | System
| FRD | Financial information | Audited Financial Report |  | Yearly | MFI | Odoo
|  |  | Balance sheet |  | Monthly,Quarterly, Annually
|  |  | Income statement |  | Monthly,Quarterly, Annually
|  |  | Ratios (Financial and Non Financial inculding PAR) |  | Monthly,Quarterly, Annually
| FRD | Progress Reports | Related information with MFI's operations such as number of clients, loans, townships, Loan Disbursements, Savings and etc. | 03/2013/TT-NHNN | Monthly,Quarterly, Annually | MFI | Terasoft
There is the format of FRD.
These information need to get from Terasoft.
| FRD | Reports | Sometimes FRD request the reports related with Clients per loan size, loan type, business and also the number of clients which live in township/ villages. |  | Based of FRD's request | MFI | Base on Terasoft

## Sheet1 (hidden)
DOCTOR CASH LIMITED
PAYMENT VOUCHER
Vr No: Bank 001
Date: 26th January 2016
Sr. No. | Description |  |  | Account Code | Amount
(Kyat/USD)
1 | Purchasing of Three Laptops from KMD
TOTAL
Paid By: |  | Check By | Approved By | Received By
Sign : |  | Sign : | Sign : | Sign :
Name : |  | Name : | Name : | Name :
Position : |  | Position : | Position : | Position :